## Risk Management Plan
| Date | 2022-12-08
| Project Mngr |  | Ioana - Teodora Dumitrescu | Tree Generation for optimal binarization evaluation
None
Priority | PROJECT RISK MANAGEMENT PLAN | [25 empty] | WBS 100 Project Management
| Identification | [5 empty] | Qualitative Analysis | [9 empty] | Quantitative Analysis |  |  |  | Response Strategy |  |  | Monitoring and Control |  |  | WBS 150 Develop Project Initiation Document (PID) | PID = Project Initiation Document
| Status | ID # | Date Identified Project Phase | Functional Assignment | Threat | Risk Trigger (Event) Description | Type | Probability | Impact | Risk Matrix | [7 empty] | Probability (%) | Impact ($ or days) | Effect ($ or days) | Strategy | Response Actions including advantages and disadvantages | Affected WBS Tasks | Responsibilty (Task Manager) | Status Interval or Milestone Check | Date, Status and Review Comments | WBS 160 Perform Preliminary Engineering Studies and Prepare Draft Project Report | PA&ED = Project Approval & Environmental Document
| Active |  | PID |  |  |  | Scope | Very High | Very High | [8 empty] | 0.9 |  |  | Avoidance | [5 empty] | WBS 165 Perform Environmental Studies and Prepare Draft Environmental Document (DED)
| Dormant |  | PA&ED |  |  |  | Schedule | High | High | [8 empty] | 0.7 |  |  | Transference | [5 empty] | WBS 175 Circulate Draft Environmental Document and Select Preferred Project Alternative
| Retired |  | PS&E |  |  |  | Cost | Moderate | Moderate | [8 empty] | 0.5 |  |  | Mitigation | [5 empty] | WBS 180 Prepare and Approve Project Report and Final Environmental Document
|  |  | Construction |  |  |  | Quality | Low | Low | [8 empty] | 0.3 |  |  | Acceptance | [5 empty] | WBS 185 Prepare Base Maps and Plan Sheets
[8 empty] | Very Low | Very Low | [8 empty] | 0.1 |  |  | N/A | [5 empty] | WBS 190 Prepare Structure Site Plans
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | [6 empty] | (12) |  | (13) | (14) =(13)x(12) | (15) | (16) | (17) | (18) | (19) | (20) | WBS 195 Right of Way Property Management and Excess Land | PS&E = Plans, Specifications & Estimate
1 | Retired | F1R1 | 2022-10-26 | Research | Low accuracy | Misunderstanding of the binarization problem. | Quality | Low | Very High | Probability | VH | [5 empty] | #REF! | 20% | 7 | 1.4 | Avoidance | Maximizing active research time (a: higher efficiency, d: late start) | WBS 150 Develop Project Initiation Document (PID) | Whole team | one week | Finished with concludent results (high accuracy) | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | #REF!
[11 empty] | M | [5 empty] | #REF!
(4): Research | L |  |  |  |  | X | #REF! | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
(4): PID | VL | [5 empty] | #REF! | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
2 | Active | F1R2 | 2022-11-02 | Development | Bugs | Miscalculations, misuse of functions, race conditions. | Quality | High | Very High | Probability | VH | [5 empty] | #REF! | 70% | 21 | 14.7 | Mitigation | Pair programming, multiple code reviews (a: low refactoring probability, d: slow development) | WBS 160 Perform Preliminary Engineering Studies and Prepare Draft Project Report | Programmers | one month | Ongoing, working on bug fixes. | WBS 230 Prepare Draft PS&E
[11 empty] | H |  |  |  |  | X | #REF!
[11 empty] | M | [5 empty] | #REF!
(4): Development | L | [5 empty] | #REF! | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
(4): Construction | VL | [5 empty] | #REF! | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package | bar: (1) to Very Low (11)
3 | Active | F2R1 | 2017-08-03 | Design | Non-optimal approach | Overly complex and slow solution. | Quality | High | Very High | Probability | VH |  |  |  |  | X | 0 | 70% | 14 | 9.8 | Acceptance | Parallelization (a: efficiency, d: refactoring) | WBS 230 Prepare Draft PS&E | Development team | one month | Ongoing, working on parallelization. | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | 0
[11 empty] | M | [5 empty] | 0
(4): Design | L | [5 empty] | 0 | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
(4): PS&E | VL | [5 empty] | 0 | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
4 | Dormant | F2R2 | 2017-09-04 | Final presentation | Product pitching | Products on the market that have higher accuracy. Unclear conclusion of the project. | Cost | Moderate | Low | Probability | VH | [5 empty] | 0 | 50% | 2 | 1 | Avoidance | Proofreading of the presentation (a: collective opinions taken into consideration, d: possible conflicting ideas) | WBS 180 Prepare and Approve Project Report and Final Environmental Document | Project Manager & Team Leader | 1 week | Dormant, to be addressed in the last phase of the project. | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | 0
[11 empty] | M |  | X |  |  |  | 0
(4): Marketing | L | [5 empty] | 0 | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
(4): PA&ED | VL | [5 empty] | 0 | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package
5 | Active | F3R1 | 2017-09-04 | Product management | Deadlines not being met | Wrong time estimations for tasks, ineffective task attributions. | Schedule | Low | Very High | Probability | VH | [5 empty] | 0 | 30% | 14 | 4.2 | Mitigation | Constant progress check, sprint meetings (a: effective teamwork & communication, d: conflicting schedules) | WBS 180 Prepare and Approve Project Report and Final Environmental Document | Project manager | 2 weeks | Ongoing, constantly checked for potential occurring problems. | WBS 230 Prepare Draft PS&E
[11 empty] | H | [5 empty] | 0
[11 empty] | M | [5 empty] | 0
(4): Product Management | L |  |  |  | X | X | 0 | [9 empty] | WBS 235 Mitigate Environmental Impacts and Clean-up Hazardous Waste
(4): PS&E | VL | [5 empty] | 0 | [9 empty] | WBS 240 Prepare Draft Structures PS&E
[12 empty] | VL | L | M | H | VH | [10 empty] | WBS 245 Post Right of Way Certification Work
[12 empty] | Impact | [14 empty] | WBS 250 Prepare Final Structures PS&E Package
WBS 255 Circulate, Review, and Prepare Final District PS&E Package